## Status Report
Status Report for Team #3 - Pet Adoption Application
Project |  | Status: (Red/Yellow/Green)
Date: | 2025-03-26 | Overall Status: | Green
Contact: | Nikkita Tarrao | Explanation: | We are on the right track right now, with everything else is on schedule.
Prepared By: | Nikkita Tarrao
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Rooshnie | Designed landing page, login page, and create account page for front end.
Nikkita | Wrote Request Service test cases. Designed the submit request page for front end.
Kris | Wrote Pet Dao test cases, added functionality to fetch and store data from the API, updated backend to support pagination of GET endpoint
Zahin | Designed view all requests for the front end
Tianjing | Finished User Controller to allow a login endpoint
ID # | Key Issues | Action Plan |  |  | Status
Critical Milestones |  | Health | Due Date | Comment/Status %
UML Diagram and FlowChart |  | Green | 2025-03-24 | 100%
Database Design using ERDs |  | Green | 2025-03-24 | 100%
Set up the database stucture and connection to API |  | Green | 2025-03-24 | 100%
Set up the application structure |  | Green | 2025-03-24 | 100%
Design test cases |  | Green | 2025-03-25 | 100%
Add basic functionality to perform CRUD operations |  | Green | 2025-03-25 | 100%
Add error handling |  | Green | 2025-03-25 | 100%
Test the testcases and fix any issues |  | Green | 2025-03-25 | 100%
Design front end interface |  | Green | 2025-03-26 | 15%
Connect front end and back end |  | Green | 2025-03-27 | 0%
Create final presentation |  | Green | 2025-03-27 | 20%
Practice final presentation |  | Green | 2025-03-27 | 0%
Stretch Goal: Adding a Scheduling System |  | Green
Green