## Status Report - 0328
Status Report for Team #3 - Pet Adoption Application
Project |  | Status: (Red/Yellow/Green)
Date: | 2025-03-28 | Overall Status: | Green
Contact: | Chenyang Su | Explanation: | On the right track right now, with everything else is on schedule.
Prepared By: | Chenyang Su
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Rooshnie | Enhanced navbar and login/register flow with role based rendering; added adoption modal and dynamic navbar based on user role
Nikkita | Added backend support and frontend page for viewing adoption requests by user id
Kris | Enhanced routing(Protected/Admin routes), access control, and 404 page
Zahin | Frontend and backend connections for view all requests
Tianjing | Added admin-only edit pet page with a form for updating pet details
ID # | Key Issues | Action Plan |  |  | Status
Critical Milestones |  | Health | Due Date | Comment/Status %
UML Diagram and FlowChart |  | Green | 2025-03-24 | 100%
Database Design using ERDs |  | Green | 2025-03-24 | 100%
Set up the database stucture and connection to API |  | Green | 2025-03-24 | 100%
Set up the application structure |  | Green | 2025-03-24 | 100%
Design test cases |  | Green | 2025-03-25 | 100%
Add basic functionality to perform CRUD operations |  | Green | 2025-03-25 | 100%
Add error handling |  | Green | 2025-03-25 | 100%
Test the testcases and fix any issues |  | Green | 2025-03-25 | 100%
Design front end interface |  | Green | 2025-03-26 | 100%
Connect front end and back end |  | Green | 2025-03-28 | 100%
Create final presentation |  | Green | 2025-03-28 | 100%
Practice final presentation |  | Green | 2025-03-28 | 100%
Green
Green