## Status Report
Status Report for Team #3 - Pet Adoption Application
Project |  | Status: (Red/Yellow/Green)
Date: | 2025-03-25 | Overall Status: | Green
Contact: |  | Explanation: | We are on the right track right now, we have slight issues for the textcases not being able to work. But everythign else is on schedule.
Prepared By: | Rooshnie Velautham
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Rooshnie | Wrote the 3 crud operations for the Request on the controller, service and dao. Also wrote testcases for the request dao files and tested Request on Postman.
Nikkita | Wrote 2 of the crud operations for the Request on the controller, service and dao, along with unit tests for request service layer.
Kris | Wrote all the CRUD operations for the Pets on the controller, service and dao and helped with the Crud operations of User. Also, imported the data from third party api.
Zahin | Wrote a few CRUD operations for User oon the controller, service and dao. Also, wrote testcases for the service and dao
Tianjing | Wrote a few CRUD operations for User oon the controller, service and dao. Also, wrote testcases for the service and dao
ID # | Key Issues | Action Plan |  |  | Status
1 | JUnit dependency not working | Try to delete the dependencies from the pom.xml and try building it again |  |  | Yellow
Critical Milestones |  | Health | Due Date | Comment/Status %
UML Diagram and FlowChart |  | Green | 2025-03-24 | 75%
Database Design using ERDs |  | Green | 2025-03-24 | 100%
Set up the database stucture and connection to API |  | Green | 2025-03-24 | 100%
Set up the application structure |  | Green | 2025-03-24 | 100%
Design test cases |  | Yellow | 2025-03-25 | 80%
Add basic functionality to perform CRUD operations |  | Green | 2025-03-25 | 90%
Add error handling |  | Green | 2025-03-25 | 80%
Test the testcases and fix any issues |  | Yellow | 2025-03-25 | 90%
Design basic front end interface |  | Green | 2025-03-26 | 0%
Design front end with CSS |  | Green | 2025-03-27 | 0%
Create final presentation |  | Green | 2025-03-27 | 0%
Practice final presentation |  | Green | 2025-03-27 | 0%
Stretch Goal: Adding a Scheduling System |  | Green